## Sprint 1
User Story | TO DO | In Progress | Impediment | To Verify | Done
Sprint 1
USER STORY | To Do | In Progress | Impediment | To Verify | Done
Day -1
To perform all form validations and complete remaining forms and then start with services part of our project | 1.Form Validation for User and Admin Login | Done | None | Done | Done
| 2.Form Validation for Payment and Cancel Ticket | Done | None | Done | Done
| 3. Registration Form connection With Service | Done | None | Done | Done
| 4.Coach Bus Form making and validation | Done | None | Done | Done
Day-2
To make changes in the Database Tables ,continue with the services part of the other forms and test with Json server. Starting the front end of our project using Spring boot | 1.testing services with Login form of user and admin | Done | None | Done | Done
| 2. testing services with Admin dashboard options | Done | None | Done | Done
| 3. Making final changes in the database tables | Done | None | Done | Done
| 4. Implementing Registration using Spring boot | Done | None | Done | Done
| 5. Implementing Bus Details using Spring Boot | Done | None | Done | Done
| 6. Testing Registration of Spring Boot using Postman | Done | None | Done | Done
Day-3
Reservation in Spring Boot and testing with Postman. Reservation in Angular and testing it with Json Server using services. Seat selection. Payment form correction. Coach Bus implementation | 1.Implementing Reservation in Spring Boot and testing with Postman | Done | None | Done | Done
| 2. Reservation checking using services with json server | Done | None | Done | Done
| 3. seat selection form and validation | Done | None | Done | Done
| 4. Payment Table making minor corrections | Done | None | Done | Done
| 5. Reservation of authorised and unauthorised user integration of Angular with Spring Boot | Done | None | Done | Done
| 6.Coach Bus implementation in Angular and integration with the Spring Boot | Done | None | Done | Done
Sprint 2
USER STORY | To Do | In Progress | Impediment | To Verify | Done
Day-4 | 1. Implementing Reservation functionality with back end and front end | Done | None | Done | Done
Reservation functionality integration of back end front end. Implementation of Payment model in the back end and connecting it with front end. | 2. Implementing Payment Model using Spring Boot and connecting using services in the Angular | Done | None | Done | Done
Day-5
Cancellation of Booked Ticket for registered user.Email sending for successful reservation. Amendments of all the forms and their respective validations. Improving the front end part | 1. Cancellation of Booked Ticket for Registered Users | Done | None | Done | Done
| 2. Implementing email sending for succesful registration | Done | None | Done | Done
| 3. Correcting all the forms in our front end | Done | None | Done | Done
Day-6
Sending email for successful cancellation of Registered user. Final front end corrections. Linking all the pages in the Front End. Linking all the tables using Services and then integrating with the Spring Boot Application in back end. | 1. To implement email sending for succesful cancellation of Booked Ticket for Registered User | Done | None | Done | Done
| 2. Final changes of HTML and CSS in all the pages in the Angular | Done | None | Done | Done
| 3. Linking all the pages in the Angular | Done | None | Done | Done
| 4.Finally testing and checking all the implemented functionalities of both front end and back end together | Done | None | Done | Done
| 5. Forgot Password implementation | Done | None | Done | Done

## Sprint 2
User Story | TO DO | In Progress | Impediment | To Verify | Done
1
2
3
4
5
6
7
8
9
| 10 | 10

## Tracker
| 21st Aug | 24th Aug | 25th Aug
Majrul
Soumya
Gaurav
Dinesh